Road Map 
to implement the EU-LAC Joint Initiative for Research and Innovation
which corresponds to the S&T part of the EU-LAC Madrid Summit Action Plan

The road map is put forward within the context of developing the "EU-LAC Knowledge Area", among others, through the EU-LAC Joint Initiative for Research and Innovation agreed at the S&T SOM in Buenos Aires, 25-26 February 2010 and endorsed by the S&T Ministerial Forum in Madrid, 14 May 2010. It incorporates key elements of an earlier draft for an implementation road map put forward by the past co-presidencies (Argentina and Spain, consolidated version 15 April 2010) and takes account of developments since. 

The Road Map is organised on the basis of the structure of the Summit Action Plan section concerning "science, research, innovation and technology". The citations from the Summit Action Plan are in italics. NB: Expected results as framed in the Summit Action Plan may need activities under different headings/objectives and might not be fully achievable within two years until the next Summit. 
The main objective in this area is to develop the “EU-LAC Knowledge Area” through: 

i) improving cooperation in research and innovation; 

ii) strengthening scientific and technological capacities, and infrastructures; 

iii) enabling sustainable research, innovation and knowledge sharing taking into account the contribution of ancestral and traditional knowledge; 

iv) boosting the use of new technologies and technology transfer underpinning sustainable socio-economic development; and 

v) fostering cooperation between both regions as regards the digital economy and the reduction of the digital divide for improving competitiveness while making social inclusion a cross-cutting issue.

An additional objective is to strengthen and develop the existing cooperation instruments.
	Original Roadmap 2011
	Activities carried out

	Action Plan Item a) Establish a regular bi-regional dialogue on science, research, technology and innovation to consolidate EU-LAC cooperation and to update common priorities, encourage mutual policy learning and ensure the proper implementation and effectiveness of cooperation instruments.
Activities: 

· Nomination of senior officials and alternates in each EU-LAC country by early 2011. 

· Senior Officials Meetings (SOMs) will be convened annually. 
· The co-chairs will ensure continuity between SOMs, notably by regular information regarding progress with implementing the road map. They will be assisted by senior officials as agreed by each region. INCONETs and other projects will support the implementation of specific actions as appropriate.
· Establish working groups between meetings to develop and enhance cooperation in the following priority areas: bioeconomy, including food security; biodiversity and climate change; ICT for meeting societal challenges; energy. 

· Establish also a cross-cutting working group on best practice and funding.

Expected Results:

(l)
Road Map defining specific targets and associated performance indicators for the implementation of the Joint Initiative will be set up and updated on a regular basis.
	Countries in both regions nominated senior officials and alternates to establish regular bi-regional dialogue.

The senior officials meeting under the EU-LAC Joint Initiative for Research and Innovation following the adoption of the Madrid Summit Action Plan, convened 28-29 March 2011 in Brussels:
· Adopted the Roadmap

· Adopted operational guidelines for the Senior Officials Meetings (SOM)
The principal way in which the EU-LAC Joint Initiative on Research and Innovation conducts its work is through thematic working groups co-led by a senior official from one country of each region. A working group on good practice and funding addresses cross-cutting issues. The working groups deal with most of the activities under the action plan items of the roadmap.

· Established four working groups (WGs) to develop pilot activities on priority themes identified for the Joint Initiative since the Buenos Aires SOM. WGs are co-led by senior official of the LAC and EU regions respectively. Namely
· Bioeconomy including food security (co-led by Argentina and France)

· Biodiversity and climate change (co-led by Colombia and France)

· ICT for meeting societal challenges (co-led by Chile and Finland)
· Energy (renewables) (co-led by Mexico and Spain).

· Established a cross-cutting working group on best practice and funding (co-led by Mexico and Portugal).

· Approximately bi-monthly updates on the advances of the working groups have been circulated to senior officials nominated to the process and participants of the Brussels SOM.

· INCONETs and other projects have supported the work of the Senior Officials WGs.

	Action Plan Item b) Explore the possibility of working jointly with other institutions in matters related to innovation and knowledge, applied research and technological innovation.

Activities:

· Develop, together with the Inter-American Development Bank (IDB), World Bank, CACYT
 and other relevant institutions, a workshop on good practices of international cooperation on science, technology and innovation, preferably in the first half of 2011. 

· Analyse programmes such as CYTED
 and the Iberoamerican Innovation Programme for proposing coordinated work. 

· Explore together with the Organisation for Economic Cooperation and Development (OECD) possible synergies relating to the “Innovation Initiative Towards Latin America”. 

· Seek other relevant opportunities for such collaboration through 2012.

Expected Results:

(p) Improved quality and effectiveness of the scientific and technological cooperation through: iv) increased information exchange.
	· Contacts with IDB have been revived by the Chilean co-chair following on from successful workshops on lessons to be learnt from innovation efforts in Latin America.
· IDB representatives participated during Bioeconomy WG 2nd. Consultation in Paris, September  2011
· ECLAC/CEPAL has participated actively in the work of the ICT WG of senior officials with particular emphasis on e-inclusion.

· OECD report has been widely circulated in view of its use in developing stronger synergies, not only with LA countries which are already members (Mexico, Chile).
· The working groups address most of the action plan activities, which are identified by way of concrete examples in the roadmap. 
· CYTED thematic networks coordinators and experts participated in WG workshops. Further coordinated work could be explored. 

· Other collaboration opportunities, such as STIC-Amsud and MATH-Amsud, has been explored for support of specific initiatives in the ICT Working Group.  



	Action Plan Item c) Commence the development and implementation of the new mechanism, the "EU-LAC Joint Initiative for Research and Innovation" combining instruments at national, regional and bi-regional level as appropriate in a complementary and synergistic manner.

Activities:

· Analyse the potential synergies between bilateral and multilateral activities in the priority areas identified in the Joint Initiative (renewable energies; environment and adaptation and mitigation of the effects of climate change; food, agriculture and food security; health with emphasis on poverty related diseases and public health systems; ICT) including the analysis of the key factors for its successful implementation and of lessons learned during its negotiation, preparation and implementation process in order to make more efficient the design of future instruments by mid-2011. Work of already on-going INCO-Nets or other types of existing projects or networks (e.g. EUROCLIMA, RALCEA) may also be considered. Activities mentioned under items a) and d) to j) of the Summit Action Plan all form part of the Joint Initiative. In order to avoid duplication, they will be addressed under the respective items in the sequence they appear in the Action Plan. 

· Create a network and a virtual platform to enhance sharing of information and experience with particular emphasis on research and innovation. This will benefit from inputs from numerous projects (European FPs and others, including preferably a wiki on key information relevant for innovation).

· Evaluate the experience of existing programme and project twinning among research programmes at different levels and the potential for extending their coverage in terms of countries, programmes and research topics (2012 and 2013).

· Evaluate coordinated research funding instruments, such as the one implemented in the EULANEST project, and identify adjustments needed for optimising their potential for promoting synergistic funding of research and innovation/development (Status report by mid 2011).

· Increase synergies between research and other cooperation programmes (e.g. bilateral research cooperations, FP7 and development cooperation as appropriate), including human resource strengthening activities (e.g. Europosgrados, different scholarship programmes) through 2012 promoting strategies to favour the return of researchers to their country of origin.

· Further refinement, for consideration by the SOM, of implementation steps for the "EU-LAC Joint Initiative for Research and Innovation", including among other aspects: (i) priority areas for cooperation; (ii) activities and instruments; (iii) funding options (through 2012).

Expected results: 

(m) A comprehensive joint strategy in research, development and innovation supporting, among other things, an improved use of the possibilities that ICT offers.

(p) Improved quality and effectiveness of the scientific and technological cooperation through: i) increased knowledge of EU-LAC scientific and technological communities; ii) increased research focus on agreed items of mutual interest; iv) increased information exchange.
	The working group on Good practice and funding has collected information about national, regional and bi-regional funding instruments. It has also started to look into other instruments available to enhance cooperation, including alignment of programmes, twinning, joint programming, mutual opening and others with potential to strengthen complementarities and synergies.
All WGs have increased the focus of where to prioritise cooperation and looked into available instruments and mechanisms to implement their priorities through a wide range of approaches.

The INCONETs and other thematic coordination projects, such as AMERICAS, support their work.

EULARINET:  http://www.eularinet.eu/

EUCARINET: http://www.eucarinet.eu/

ENLACE: http://www.enlace-project.eu/

AMERICAS: http://www.americasproject.eu/
ALCUE KBBE: http://www.bioeconomy-alcue.org/

ALCUE Health: www.eulachealth.eu. EU-LAC Health is a project funded by FP7 aiming at defining a road-map for cooperative health research between the EU (and its Member States) and LAC countries (https://sites.google.com/a/eulachealth.eu/eulac-health-project/home). EU-LAC Health will last for five years in order to guarantee an effective and sustainable cooperation.
Within FP7-INCO-2012-1 EC Call a Project named “ALCUENET” integrated by a biregional consortium of relevant ST&I organizations was submitted in order to mainly support EULAC JIRI implementation during 2012-2016.

Regional projects funded by Development Cooperation Instruments (DCI) are also directly relevant to the objectives of the Joint Initiative and its concern for better combination of existing instruments, projects and programmes:

EUROCLIMA: Climate change regional cooperation programme: http://ec.europa.eu/europeaid/where/latin-america/regional-cooperation/euroclima/index_en.htm
ALICE2 project: http://alice2.redclara.net/index.php/en/project/lis2-programme
The working group on cross-cutting issues 'Good practice and funding' has compiled an initial table of funding instruments used, including ERANETs, such as EULANEST Joint Call, as well as Twinnings and Coordinated Calls. 

The thematic working groups have narrowed down further the priority areas for cooperation, the type of activities and instruments most relevant to achieve the objectives and explored funding options for implementation. 
The Thematic Programme for Environment and Sustainable Management of Natural Resources including Energy (ENRTP), Art 21 04 06 - Water Management in Developing Countries in favour of Latin American Region, constituted by the action “Latin American Network of knowledge centres in the water sector (RALCEA Project)", the text of which is set out in the attached Annex is approved. The maximum contribution of the European Union to the Action is set at 2 Million EUR to be financed from budget line pilot projects 21 04 06 of the general budget of the European Communities for 2009: http://ec.europa.eu/europeaid/where/latin-america/regional-cooperation/ralcea/index_en.htm 
In Latin America, the six axes of the Guanajuato Action Plan are being implemented, including the PILAC Initiative, cooperation in thematic areas and research infrastructures, political dialogue and internationalization of S&T in the LAC region. The next Latin American ministerial and senior official meeting in S&T will be held in Brazil in May 2012.

In the framework of UNASUR, the Working Group of Science and Technology in the South American Council of Education, Culture, Science, Technology and Innovation (COSECCTI) has created a permanent communication channel among high representatives in S&T in the region with regular meetings and specific initiatives, such as the manual gathering information on all national STI systems in UNASUR.
In the framework of CELAC, Chile presented a document aimed at assessing the various S&T cooperation mechanisms and institutionalized political dialogues working in Latin America and the Caribbean, increasing synergies and calling for funding of the initiatives promoted by these mechanisms. 

EUROPOSGRADOS 2012: A number of meetings and workshops will be organized in Argentina called “Tour 2012” to promote mobility and scholarships programs for students, professors and researchers between European and LAC Universities from both directions in Cordoba, Mendoza, Tucuman and Neuquen Provinces (April-May 2012)


	Action Plan Item d) Establish or strengthen thematic networks on agreed issues of mutual interest, which should facilitate exchanges between EU-LAC universities and research centres and networks and private and public sector institutions.

Activities: 

· Identification of synergies between existing promotional networks already animated through promotional and networking projects (EULARINET, ENLACE, EUCARINET, FIRST, PRO-IDEAL Plus, follow-up to ALCUE Food, ELAN2Life, EUROCLIMA, RALCEA and others) and how they can contribute to the development and strengthening of more specific initiatives and identified strategic issues (through 2012). 

· Develop further project and programme twinning in priority areas of cooperation through 2012.

· Promote networking around social participation, synergistic use of scientific and local knowledge and integration of ICT (through technology capacity building) into generation of new knowledge and use for innovation, continuous through 2012. 

Expected Results:

(p)
Improved quality and effectiveness of the scientific and technological cooperation through i) increased knowledge of EU-LAC scientific and technological communities; ii) increased research focus on agreed items of mutual interest; iv) increased information exchange.
	A number of meetings and workshops have already connected some of the platforms and support projects. 

Moreover, programmes like ALFA III, IRSES (staff exchange between research institutions in LA and EU), bilateral and national scholarship programmes facilitate exchanges between EU-LAC universities, research centres and networks, both public and private sector institutions. Difficult to quantify the scale, however.
The ICT support action project FIRST (2010-2011) has initiated and supported the establishment of ICT Technology Platforms in Argentina, Brazil, Chile, Colombia and Mexico, and brought their leaders together with the corresponding European Technology Platforms in the area of ICT during the Future Internet Week in October 2011 in Poznan/Poland. This is likely to lead to closer collaboration between European and Latin American Technology Platforms in the future. Furthermore, a possible development could be the establishment of one or more overall Latin American Technology Platforms (e.g. in areas corresponding to ETPs).

The working groups address most of the action plan activities, which are identified by way of concrete examples in the roadmap working towards stronger networking with existing platforms, project, programmes and initiatives.

	Action Plan Item e) Strengthening the integration of both regions in the Information Society and support the development of the information and communication technologies (ICT) sector and the reduction of the digital divide and digital illiteracy through an increase of interconnectivity between the education and research networks within and between regions and enhance access to and use of resources.
Activities:

· Consolidation and extension of RedCLARA 2 network for improving the access of Latin American countries to e-infrastructures, with a special focus on reaching Latin American and Caribbean regions which present a lower level of progress in this aspect, on-going through 2012.  

· Support action for the feasibility study of new submarine optic fibre cables between Latin America and Europe starting in 2011.

Enhanced collaboration and interoperability between the European Spatial Data Infrastructure (INSPIRE) and national/regional efforts in Latin America / the Caribbean, e.g. the Spatial Data Infrastructure for the Americas (IDEA). 

Expected Results:

(m) A comprehensive joint strategy in research, development and innovation supporting, among other things, an improved use of the possibilities that ICT offers, including in the areas of e-Government, e-Health and e-Education, as well as in relation to climate change-related and other relevant issues.
(n) Reinforced private and public sector efforts for the improvements of the interconnection of education and research networks through the enhancement of transatlantic links, including through new optic fibre cables.
	RedCLARA has consolidated and extended its network. It also supported video-conferencing across LA countries (around 100 connected points) in 2010 and 2011 immediately after publication of the new FP7 work programmes.
RedCLARA furthermore improved and enhanced the interactive platform of virtual communities, aimed at developing capacities, skills and collaboration through ICT tools among different communities in Latin America.
A feasibility study on a new sub-marine optic fibre cable connecting Latin America and Europe is ongoing (FP7 e-Infrastructures project ELLA).
The ICT Working Group has addressed issues such as e-Health and e-Inclusion and proposed concrete actions in the field oriented towards an impact in vulnerable and rural areas. 
ECLAC, through its Technical Secretariat, continued implementing the eLAC2015 Action Plan on Information and Knowledge Society and held various coordination and working group meetings, defining the action plan for 2012 and indicators for progress.
In this context, nine Latin American countries met in Santo Domingo in November 2011 and defined a series of indicators aimed at measuring the progress of information and communication technologies (ICT) in Latin America and the Caribbean.


	Action Plan Item f) Develop and intensify the dialogue and cooperation on information society, strategies, regulation models for the communication sector and in the audiovisual field.

Activities:

· Regular bi-regional dialogues of telecommunication regulators and ICT policies supported by @LIS 2 programme, on-going through 2012.

· Promote the extension of the results of ICT projects and technological platforms (e.g. FIRST) to the region as a whole.

Expected Results:

(o) Increased compatibility of regulatory frameworks in the field of electronic communications and improved quality of digital contents.
	Regulatory bi-regional dialogue on information society is supported under the @lis 2 Programme. An extension of the implementation period for this programme has been requested and is currently under consideration.  
It is envisaged that the five ICT Technology Platforms created in LA countries (Argentina, Brazil, Chile, Colombia and Mexico) under the FIRST project (completed in 2011) will consolidate and continue networking with their European counterparts.

	Action Plan Item g) Develop an interface between research and innovation through a knowledge and innovation centres' network to facilitate social appropriation of knowledge and technology in particular keeping in mind the micro and SMEs.

Activities:

· Establish a Knowledge and Innovation Centre in order to network relevant existing actors and projects through strengthening the interface between research and innovation, including with EU funding by early 2012.

· Learn from innovation practice and experience through easily accessible documentation, workshops (e.g. EULARINET workshop in Uruguay, March 2010, IDB workshop, November 2010 in Buenos Aires), innovation forums (annual events in Uruguay on Pan-American basis open to Europe) and other opportunities throughout 2011 and 2012.

· Extend the development of the Biotec-EU-MERCOSUR project with particular attention to networks, incubators and technology parks, to be analysed and made available by early 2011 and kept under review for updating through 2012.

· Promote the formation of (joint) learning and research centres of excellence between EU-LAC partners, on an on-going basis through 2012, such as is the case with a German-Chile centre of excellence, the "Fraunhofer Center for Systems Biotechnology" and others in Latin American and Caribbean countries.

· Promote the establishment and/or strengthening of science and technology parks in Latin America, including for strengthening focal areas of EU-LAC entrepreneurial cooperation and keeping a higher percentage of LAC human resources within the region and therefore increasing attractiveness of cooperation, on an on-going basis through 2012.

· Enhance collaboration between the European Commission's Joint Research Centre (JRC) and Latin American / Caribbean countries in agreed strategic areas of common interest.

Expected Results:

(k)
New initiatives for more effective coordination and cooperation aiming at interconnecting knowledge, science; research and innovation; as well as business, entrepreneurial, and research centres and networks from the EU and LAC countries, and leading to an improved uptake and dissemination of research results for innovation, in particular for micro and SMEs. 
	The ICI+ funding instrument has been established and preparations need to be launched soonest to develop an operational proposal for a knowledge and innovation centres' network.
Several bi-lateral centres of excellence have been or are being established between LAC and EU countries in addition to the example mentioned in the roadmap. As examples, Wageningen UR and INRIA established centres of excellence in Chile, and in Argentina, a Bilateral Center on Biomedicine was established in collaboration with the Max Planck Society of Germany, together with centres on Industrial Design with Italy, on Plant Biotechnology with Spain, and on Modelisation with France.
A new Partnering Initiative in sustainable agriculture is under establishment between LAC and EU countries, which will allocate significant resources to a joint project in this specific area of KBBE. 
BIOTECSUR Platform 2nd. Phase was already approved by the EC and the MERCOSUR Group, implementing activities by next July 2012. The focus will be oriented towards innovation and technology transfer issues and partnership consortia building on the prioritized areas of Health and Bioenergy.

JRC representatives could be invited to participate in next events organized by thematic WGs in order to explore further collaboration opportunities.



	Action Plan Item h) Promote the extension of scientific and technological cooperation within all Latin American sub-regions and the Caribbean, as well as the adoption of innovative instruments to strengthen cooperation with special attention to countries with low participation in EU-LAC Science and Technology cooperation activities.

Activities:

· EU-LAC focus in 2011 work programmes of FP7 with broad-based information activities including video-conferences, a specific EU-LAC InfoDay and mobilisation of FP7 contacts throughout Europe and Latin America and the Caribbean particularly between July and October 2010.

· Consolidate thematic FP7 contacts in all LAC countries and continue training and networking to build local capacity in support of their research teams' participation in FP7 and the integration of LAC researchers and institutions in the European Research Area. 

· Liaison offices with longer experience will continue extending support to others in LAC countries as part of the regularly on-going activities; use of on-line courses will be encouraged, e.g. the 'Project Angel' concept practiced by the PRO-IDEAL project in ICT.

· Explore multilateral twinning throughout 2012.

· Promote the participation of LAC researchers as observers in FP7 projects in order to involve them into research networks and to build capacities to attend future research calls. 

Expected Results:

(p)
Improved quality and effectiveness of the scientific and technological cooperation through i) increased knowledge of EU-LAC scientific and technological communities; ii) increased research focus on agreed items of mutual interest; iv) increased information exchange.
	Bilateral S&T cooperation has advanced between several EU and LAC countries. In FP7, the participation of LAC countries has progressed numerically compared to FP6.
In July 2010 and 2011, in collaboration with RedCLARA, several video-conferences were carried out to inform the roughly 100 connected points across Latin America of the upcoming collaborative opportunities in the 2011 and 2012 FP7 work programmes respectively.

All LAC INCO NCPs were specifically informed and kept updated about participation of research teams of their countries.

Similar information efforts can be envisaged at the time of publishing the 2013 work programme of FP7.

The AMERICAS project (follow-up of PRO-IDEAL PLUS) ensures continuity of the Project Angels network in the ICT area, and foresees continued trainings (e.g. summer schools).
Matchmaking event on KBBE in Toulouse within EULARINET+ABEST Projects. (Training course+FP7 Calls dissemination)

An important number of INFO DAYS were organized in 2011 and will be organized in 2012 by Liaison Offices from LAC countries in order to disseminate FP7 Calls, with active participation of thematic NCPs.


	Action Plan Item i) Foster cooperation for human and institutional capacity building and encourage the return of researchers to their countries of origin.

Activities:

· Promotion of LAC participation in all types of Marie Curie Actions of individual and institutional research grants; the international incoming fellowships (IIF) foresee the possibility of funding for reintegration grants for returning researchers; specific attention should be paid to the two under-utilised schemes “Industry-Academia Partnerships” and “Initial Training Networks” (ITN) in the 2011 and 2012 work programmes of FP7 (People Programme).

· Promote full use of the Erasmus Mundus Programme 

· Continuation of the Europosgrados events and associated programmes for student and researcher mobility of EU Member States and LA countries through 2012.

· S&T capacity building in Caribbean countries through the relevant EDF project, running through 2012.

· National and/or collaborative capacity building programmes in S&T&I in several countries.

· Joint PhD programmes between EU and LAC countries' higher education institutions through 2012.

· Promote the mutual access to research infrastructures in agreed areas of common interest as well as the development of joint infrastructure initiatives. 

· Foster the role of the European Commission's Joint Research Centre (JRC) in training and capacity building of scientists and administrators in Latin America and the Caribbean. 

· Strengthening and developing the existing instruments is important. 

Expected Results:

(p)
Improved quality and effectiveness of the scientific and technological cooperation through i) increased knowledge of EU-LAC scientific and technological communities; iii) larger scientific and technological capacities of LAC countries, involving also national programmes and capacity building for the Caribbean, to drive their own development and to achieve enhanced cooperation opportunities with the EU; iv) increased information exchange.
	The working groups address most of the action plan activities, which are identified by way of concrete examples in the roadmap.

Scholarship programmes for building up advanced human capital exist at the level of LAC and EU countries.
At the European level, Marie Curie Actions in the People Programme have contributed to the Action Plan.
EUCARINET (INCONET for the Caribbean) has promoted use of these and other opportunities for capacity building in the Caribbean region.

The Bioeconomy WG has proposed a Biregional Master Program in Bioeconomy with the objective of increasing capacity building and human resources development in LAC countries.

	Action Plan Item j) Exchange experiences and best practices in areas of innovation, such as incubation, entrepreneurship, science parks and start-up enterprises.

Activities:

· Use of results of INCONETs workshops and analyses for supporting a more structured process of learning about innovation experiences and their applicability in different situations in EU and LAC countries.

· Convene one or more workshops through inter-institutional collaboration to support broader-based learning in these areas.

· Participation in the LA Innovation Forum in Uruguay in 2011 and other such initiatives.

· Strengthening and developing the existing instruments is important. 

Expected Results:

(k)
New initiatives for more effective coordination and cooperation aiming at interconnecting knowledge, science; research and innovation; as well as business, entrepreneurial, and research centres and networks from the EU and LAC countries, and leading to an improved uptake and dissemination of research results for innovation, in particular for micro and SMEs. 

(p)
Improved quality and effectiveness of the scientific and technological cooperation through i) increased knowledge of EU-LAC scientific and technological communities; ii) increased research focus on agreed items of mutual interest; iv) increased information exchange.
	The working groups address most of the action plan activities, which are identified by way of concrete examples in the roadmap.

Stronger emphasis on innovation in the regional AL-INVEST Programme in 2010 and 2011 has contributed to this objective of the Action Plan.
Chile and Mexico are already participants in the Entreprise Europe Network and Argentina is in the last preparatory stage before joining.

See also Action Plan item i)

The five technology platforms established with the help of the FIRST project in Argentina, Brazil, Chile, Colombia and Mexico, have good potential to contribute to interconnecting knowledge, research and innovation and connect businesses in Latin America and to the European technology platforms. 

The establishment of national Living Labs organisations in Latin American countries, and of an overall Latin American Living Labs organisation could open new opportunities for cooperation with Europe (e.g. the European Network of Living Labs/ENoLL). The ICT Working Group will work towards the implementation of a Latin American network of Living Labs and encourage the establishment of Living Labs in the LAC countries.



� CACYT is the Council of Science and Technology of the Community of Andean countries


� CYTED is the 'Programa Ibero-Americano de Ciencia y Tecnología'
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